PROGRAM MANAGEMENT CASE STUDY

Inventory Audit & Cycle Count Process

Reducing Shrinkage Through Structured Inventory Counts at a Retail Jewelry Store

Prepared by: Dimple Manda

Role: Program Manager

[Month Year]

# Executive Summary

This case study documents a program to design and implement a structured cycle-counting process for high-value jewelry inventory, replacing a single annual full count with a rolling, category-based audit schedule. It reflects program management practices scoped to a project a coordinator could own directly — from process design through measured reduction in inventory discrepancies. Figures and names below are illustrative; the approach mirrors real program management practice applicable to any retail inventory-accuracy initiative.

# 1. Project Charter

## Background

The store relied on a single full physical inventory count once a year, meaning discrepancies — misplaced items, data entry errors, or potential shrinkage — often went unnoticed for months. By the time the annual count surfaced an issue, it was difficult to trace the cause, and the count itself took the whole team a full weekend to complete, disrupting normal operations.

## Objective

Design and implement a rolling cycle-count process — auditing a rotating subset of inventory categories weekly — to catch discrepancies early, reduce the annual count's disruption, and build a more accurate, continuously-verified inventory record.

## Scope

- In scope: define inventory categories and count rotation schedule, build a simple count/reconciliation worksheet, train staff on the counting and discrepancy-logging process, run a 6-week pilot rotation covering all categories once.

- Out of scope: RFID or barcode-scanning hardware investment, replacing the annual full count entirely, integration with a new inventory management system.

## Key Details

Sponsor:  Store Manager

Program Manager:  Dimple Manda

Timeline:  6 weeks (design through first full rotation)

Budget:  $600

Success Metrics:  100% of inventory categories cycle-counted at least once in the pilot · Discrepancies identified and resolved within 5 business days of being logged · Reduced time required for the next annual full count

# 2. Stakeholder Map

Given the sensitivity of high-value inventory, clear ownership of counting and discrepancy escalation was central to the process design.

| Stakeholder | Interest / Role | Influence | Engagement Approach |
| --- | --- | --- | --- |
| Store Manager | Sponsor; approves count schedule and reviews discrepancies | High | Weekly discrepancy review meeting |
| Sales Associates | Perform the counts on a rotating basis | Medium | Trained on count worksheet and process during rollout |
| Bookkeeper | Reconciles discrepancies against financial and insurance records | Medium | Consulted on discrepancy escalation process |
| Store Owner / GM | Interested in shrinkage reduction and insurance accuracy | Medium | Summary update at end of pilot rotation |

# 3. RAID Log (Risks, Assumptions, Issues, Dependencies)

Kept lightweight given the project's scale, but tracked actively to refine the process during the pilot rotation.

| Type | Description | Likelihood / Impact | Owner | Mitigation / Response |
| --- | --- | --- | --- | --- |
| Risk | Weekly counts disrupt regular floor coverage during busy periods | Medium / Medium | Store Manager | Scheduled counts during historically low-traffic hours |
| Risk | Inconsistent counting method between associates leads to inaccurate discrepancy data | Medium / Medium | Program Manager | Standardized count worksheet with clear step-by-step instructions |
| Assumption | Existing inventory categories in the POS system are granular enough to support rotation | — | Program Manager | Confirmed category structure before finalizing rotation schedule |
| Issue | Example: first cycle count uncovered a mislabeled category with mixed item types | — | Store Manager | Recategorized items and updated the count worksheet before next rotation |
| Dependency | Staff must be trained on the new count worksheet before the first scheduled count | — | Program Manager | Training session scheduled the week before pilot launch |

# 4. Budget Summary

| Category | Planned | Actual | Notes |
| --- | --- | --- | --- |
| Program manager design time (in-house) | $400 | $400 | Process design and worksheet creation |
| Staff time for weekly counts (incremental) | $150 | $140 | Roughly 1 hour/week across rotation |
| Printed count worksheets | $30 | $25 | On budget |
| Contingency | $20 | $10 | Minor reprints |
| TOTAL | $600 | $575 | Actuals reflect time and materials through pilot rotation |

# 5. Communications Plan

| Audience | Channel | Frequency | Content |
| --- | --- | --- | --- |
| Store Manager | Discrepancy review meeting | Weekly | Count results, discrepancies found, resolution status |
| Sales Associates | Team huddle + printed worksheet | Once, before pilot start; ongoing reference | Counting method and discrepancy logging process |
| Bookkeeper | Shared log | As discrepancies arise | Financial/insurance reconciliation of flagged items |
| Store Owner / GM | Short summary | End of pilot rotation | Results and recommendation to continue |

# 6. Post-Launch Review

## Outcomes

- All inventory categories were cycle-counted at least once within the 6-week pilot rotation.

- Three discrepancies were identified and resolved, all within the 5-business-day target.

- Early feedback suggested the next annual full count would take meaningfully less time given the more current baseline.

## What Went Well

- Scheduling counts during low-traffic hours avoided disrupting customer-facing operations.

- A standardized worksheet made discrepancy patterns easier to spot across different counters.

## Lessons Learned

- Verify category definitions in the source system before designing the rotation — a mislabeled category caused early rework.

- A short weekly discrepancy review meeting kept issues from piling up unresolved.

## Next Steps

Recommended next step: formalize the cycle count as an ongoing monthly rotation rather than a one-time pilot, and evaluate barcode scanning as a future accuracy and speed improvement.

# 7. Program Management Skills Demonstrated

- Process design and standardization

- Stakeholder engagement across operations and finance

- Lightweight risk and issue management

- Schedule and resource planning around live operations

- Data accuracy and reconciliation practices

- Pilot design and outcome measurement