PROGRAM MANAGEMENT CASE STUDY

Staff Onboarding & Training Program

Building a Structured New-Hire Program for a Retail Jewelry Store

Prepared by: Dimple Manda

Role: Program Manager

[Month Year]

# Executive Summary

This case study documents a program to design and roll out a structured onboarding and training curriculum for new store hires, replacing an informal, inconsistent shadow-training approach. It reflects program management practices scoped to a project a coordinator or junior program manager could own directly — from defining the training structure through measuring its impact on new-hire readiness. Figures and names below are illustrative; the approach mirrors real program management practice applicable to any retail onboarding improvement.

# 1. Project Charter

## Background

New hires were trained informally by shadowing whichever associate was available that day, with no standard checklist or sequence. Coverage of key topics — POS operation, product knowledge, loss prevention, and customer service standards for high-value merchandise — varied significantly by who trained them. This led to inconsistent readiness, longer ramp-up time, and occasional process errors (like mishandling repair intake) in a new hire's first weeks.

## Objective

Design and roll out a structured onboarding and training program with a consistent curriculum, checklist, and timeline — reducing new-hire ramp-up time and ensuring every associate reaches full floor-readiness with the same baseline knowledge.

## Scope

- In scope: define core training topics and sequence, build a new-hire checklist and training schedule, create simple reference materials (quick guides), train existing staff to deliver it consistently, pilot with the next two new hires.

- Out of scope: formal LMS software purchase, corporate-wide rollout beyond this store, compensation/role changes tied to training completion.

## Key Details

Sponsor:  Store Manager

Program Manager:  Dimple Manda

Timeline:  5 weeks to design and pilot

Budget:  $1,400

Success Metrics:  New-hire time-to-floor-readiness reduced by 40% · 100% of pilot hires complete the full checklist · Zero process errors related to missed training topics in first 30 days

# 2. Stakeholder Map

Mapping who shapes and delivers the training program clarified where to focus design time versus where to simply keep people informed.

| Stakeholder | Interest / Role | Influence | Engagement Approach |
| --- | --- | --- | --- |
| Store Manager | Sponsor; approves curriculum and schedule | High | Weekly check-ins during design; sign-off before pilot |
| Senior Sales Associates | Deliver hands-on training to new hires | High | Involved in curriculum design; trained as designated trainers |
| New Hires (pilot group) | End users of the new onboarding experience | Medium | Feedback survey after first 30 days |
| Store Owner / GM | Interested in reduced ramp-up time and error rates | Medium | Summary update at pilot completion |

# 3. RAID Log (Risks, Assumptions, Issues, Dependencies)

Kept lightweight given the project's scale, but tracked actively to keep the pilot on track.

| Type | Description | Likelihood / Impact | Owner | Mitigation / Response |
| --- | --- | --- | --- | --- |
| Risk | Designated trainers fall back to old informal habits under time pressure on busy days | Medium / Medium | Store Manager | Kept checklist short and laminated for quick reference on the floor |
| Risk | New hire feels overwhelmed if entire curriculum is front-loaded in week one | Medium / Low | Program Manager | Spread curriculum across a structured two-week schedule rather than day one |
| Assumption | Two new hires would be starting within the pilot window to test the program | — | Store Manager | Confirmed hiring timeline before finalizing pilot schedule |
| Issue | Example: first pilot hire's schedule didn't align with the trainer's shifts | — | Store Manager | Adjusted trainer assignment to match new hire's actual shift pattern |
| Dependency | Reference guides must be finished before the first pilot hire's start date | — | Program Manager | Materials completed one week ahead of pilot start as a buffer |

# 4. Budget Summary

| Category | Planned | Actual | Notes |
| --- | --- | --- | --- |
| Program manager design time (in-house) | $900 | $900 | Curriculum design and materials creation |
| Trainer time (senior associates, paid hours) | $350 | $320 | Slightly under due to schedule alignment fix |
| Printed materials (checklists, quick guides) | $100 | $85 | On budget |
| Contingency | $50 | $20 | Minor reprints |
| TOTAL | $1,400 | $1,325 | Actuals reflect time and materials through pilot completion |

# 5. Communications Plan

| Audience | Channel | Frequency | Content |
| --- | --- | --- | --- |
| Store Manager | In-person check-in | Weekly during design | Curriculum review, schedule approval |
| Senior Associates / Trainers | Team huddle | Once, before pilot start | Trainer responsibilities and materials walkthrough |
| Pilot New Hires | In-person, day one | Start of employment | Program overview and checklist walkthrough |
| Store Owner / GM | Short summary | End of pilot | Results and recommendation to continue |

# 6. Post-Launch Review

## Outcomes

- Both pilot hires completed the full training checklist within their first two weeks.

- Time to full floor-readiness dropped from an estimated 3–4 weeks to under 2 weeks.

- No process errors related to missed training topics were reported in the pilot hires' first 30 days.

## What Went Well

- Involving senior associates in curriculum design increased their buy-in as trainers.

- Spreading the schedule over two weeks, rather than front-loading, kept new hires from feeling overwhelmed.

## Lessons Learned

- Confirm trainer shift alignment with the new hire's schedule before finalizing the training plan, not after.

- A short, laminated checklist got used far more consistently on the floor than a longer written guide.

## Next Steps

Recommended next step: formalize the program as the standard onboarding process for all future hires, and revisit the curriculum quarterly as product lines or POS processes change.

# 7. Program Management Skills Demonstrated

- Scoping and chartering a self-led initiative

- Stakeholder engagement and buy-in building

- Curriculum design and process standardization

- Lightweight risk and issue management

- Pilot design and outcome measurement

- Change management and staff enablement