PROGRAM MANAGEMENT CASE STUDY

Store Performance Reporting Dashboard

Automating Weekly Sales & Inventory Reporting for a Retail Jewelry Store

Prepared by: Dimple Manda

Role: Program Manager

[Month Year]

# Executive Summary

This case study documents a smaller-scale, self-led program to design and implement an automated weekly performance reporting dashboard for a retail jewelry store. It reflects the same program management discipline applied on larger initiatives — a clear charter, stakeholder alignment, risk management, and post-launch review — scoped to a project one person can own and deliver in a few weeks. Figures and names below are illustrative; the approach mirrors real program management practice applicable to any store-level reporting improvement.

# 1. Project Charter

## Background

Each week, the store manager spent roughly three hours manually pulling sales, inventory, and staff-hours data from separate exports and combining them into a spreadsheet for the Monday leadership review. The process was time-consuming, error-prone, and delayed decisions on markdowns, restocking, and staffing — by the time the report was ready, the data was already several days old.

## Objective

Design and implement an automated weekly reporting dashboard that consolidates sales, inventory turnover, and staff performance data into a single view — cutting report preparation time by over 80% and giving leadership same-day visibility into store performance.

## Scope

- In scope: define key metrics with store leadership, build a consolidated data workbook from existing POS/inventory exports, design a clear one-page dashboard view, automate weekly refresh with formulas, train the store manager on use and upkeep.

- Out of scope: purchasing a dedicated BI platform license, integrating directly with corporate systems, historical reporting beyond the trailing 12 months.

## Key Details

Sponsor:  Store Manager

Program Manager:  Dimple Manda

Timeline:  6 weeks

Budget:  $2,800

Success Metrics:  Weekly report prep time reduced from ~3 hours to under 30 minutes · Dashboard adopted as the standard tool for weekly leadership review · Zero data errors identified in first month of use

# 2. Stakeholder Map

Even a small, self-led project benefits from a clear view of who's affected and how much say they have in shaping it.

| Stakeholder | Interest / Role | Influence | Engagement Approach |
| --- | --- | --- | --- |
| Store Manager | Primary user of the dashboard; sponsor of the initiative | High | Weekly working sessions to define metrics and review drafts |
| Store Owner / GM | Uses dashboard output for broader business decisions | Medium | Demo at project midpoint and final walkthrough at launch |
| Sales Associates | Source of daily sales and hours data feeding the report | Low | Brief explanation of why data entry consistency matters |
| Bookkeeper | Validates that financial figures match accounting records | Medium | Consulted during metric definition and final validation |

# 3. RAID Log (Risks, Assumptions, Issues, Dependencies)

Kept lightweight given the project's scale, but still used actively to stay ahead of problems.

| Type | Description | Likelihood / Impact | Owner | Mitigation / Response |
| --- | --- | --- | --- | --- |
| Risk | Inconsistent POS export formatting breaks the automated formulas | Medium / Medium | Program Manager | Built input-validation checks; standardized the weekly export steps into a checklist |
| Risk | Store manager reverts to old manual process if dashboard feels unfamiliar | Medium / Medium | Program Manager | Kept the layout close to the familiar report format; provided a one-page quick guide |
| Assumption | POS system can export sales and inventory data on a consistent weekly schedule | — | Program Manager | Confirmed export capability and format before building formulas |
| Issue | Example: initial data export didn't include staff hours needed for a labor-efficiency metric | — | Program Manager | Added a manual weekly hours entry field as a lightweight workaround |
| Dependency | Metric definitions must be agreed with the store manager before the dashboard layout is built | — | Store Manager | Metrics workshop scheduled in week 1, ahead of any build work |

# 4. Budget Summary

| Category | Planned | Actual | Notes |
| --- | --- | --- | --- |
| Software (existing Excel/Power BI license) | $0 | $0 | Used tools already available to the store |
| Program manager time (build & training, in-house) | $2,200 | $2,200 | Estimated at internal hourly rate |
| Staff training time | $300 | $250 | One 45-minute working session with store manager |
| Contingency | $300 | $100 | Covered minor formula rework after week-2 feedback |
| TOTAL | $2,800 | $2,550 | Actuals reflect time and materials through launch |

# 5. Communications Plan

| Audience | Channel | Frequency | Content |
| --- | --- | --- | --- |
| Store Manager | In-person working session | Weekly | Metric review, draft feedback, adoption check-in |
| Store Owner / GM | Short demo | Midpoint + launch | Progress update and final walkthrough |
| Sales Associates | Team huddle | Once, at rollout | Why consistent data entry matters for the new report |

# 6. Post-Launch Review

## Outcomes

- Weekly report preparation time dropped from approximately 3 hours to under 25 minutes.

- The dashboard became the standard reference in every Monday leadership review within the first month.

- No data errors were identified in the dashboard output during the first month of use.

## What Went Well

- Defining metrics together with the store manager up front avoided rework later — the first draft was close to final.

- Keeping the dashboard layout visually close to the old manual report reduced resistance to adopting it.

## Lessons Learned

- Always confirm every data field needed (like staff hours) before finalizing scope — a missing field found mid-build caused avoidable rework.

- A simple one-page quick-reference guide made adoption smoother than relying on a single training session alone.

## Next Steps

Recommended next step: extend the dashboard with a rolling month-over-month trend view, and evaluate whether a low-cost BI tool would be worth adopting as the store's reporting needs grow.

# 7. Program Management Skills Demonstrated

- Scoping and chartering a self-led initiative

- Stakeholder engagement on a small scale

- Lightweight risk and issue management

- Budget discipline on a limited-resource project

- Change management and user adoption

- Process improvement and time-savings measurement