PROGRAM MANAGEMENT CASE STUDY

E-Commerce Platform Launch

An Integrated Online Store for a Retail Jewelry Business

Prepared by: Dimple Manda

Role: Program Manager

[Month Year]

# Executive Summary

This case study documents the plan and execution approach for launching an e-commerce platform for a retail jewelry business, integrated in real time with in-store inventory and point-of-sale data. It reflects program management practices applied across platform selection, cross-functional coordination, risk management, budgeting, and post-launch evaluation. Figures and names below are illustrative; the approach mirrors real program management practice applicable to any retail digital-launch program.

# 1. Project Charter

## Background

The store's only digital presence was a static catalog page with no purchasing capability, inventory visibility, or online reservation option. Competitors offered online browsing and buy-online-pickup-in-store (BOPIS), and the business was losing sales to customers who researched elsewhere before buying. High-value jewelry inventory also made real-time stock accuracy and secure payment processing critical requirements for any online sales channel.

## Objective

Launch a fully integrated e-commerce platform, synced in real time with in-store inventory and POS data, enabling online browsing, secure checkout, and buy-online-pickup-in-store — live within 16 weeks and within budget, with zero inventory oversell incidents at launch.

## Scope

- In scope: e-commerce platform selection and setup, real-time inventory sync integration, secure payment gateway (PCI-compliant), product photography and catalog build, BOPIS fulfillment workflow, staff training, launch marketing.

- Out of scope: custom mobile app development, loyalty program redesign, international shipping, multi-currency support (Phase 2 candidates).

## Key Details

Sponsor:  Store Owner / General Manager

Program Manager:  Dimple Manda

Timeline:  16 weeks (platform selection through post-launch review)

Budget:  $52,000 (see Section 4)

Success Metrics:  Launch on schedule and within budget · Zero inventory oversell incidents in first 60 days · Checkout success rate above 98% · At least 25% of online orders fulfilled via in-store pickup within first month

# 2. Stakeholder Map

Mapping who is affected by the launch — and their influence over its success — shaped the engagement and training plan below.

| Stakeholder | Interest / Role | Influence | Engagement Approach |
| --- | --- | --- | --- |
| Store Owner / GM | Budget approval, brand and revenue owner | High | Weekly status briefing; sign-off at each phase gate |
| Store Manager | Fulfillment operations, staff scheduling for BOPIS | High | Bi-weekly syncs; primary contact for in-store fulfillment workflow |
| Marketing Lead | Product catalog, photography, launch campaign | High | Weekly working sessions during content build and launch prep |
| Platform Vendor / Developer | Platform configuration, inventory sync, payment integration | High | Weekly technical check-ins; shared implementation tracker |
| Sales & Fulfillment Staff | Pack/prepare BOPIS orders; assist online-informed customers | Medium | Hands-on training; quick-reference fulfillment guide |
| Customers | End users of the new store; expect accurate stock and secure checkout | Low (indirect) | Beta preview list; launch announcement via email and in-store signage |

# 3. RAID Log (Risks, Assumptions, Issues, Dependencies)

A living log used throughout the program to track and respond to risks proactively rather than reactively.

| Type | Description | Likelihood / Impact | Owner | Mitigation / Response |
| --- | --- | --- | --- | --- |
| Risk | Inventory sync errors between online store and POS cause overselling of one-of-a-kind pieces | Medium / High | Program Manager | Real-time API sync with 5-minute refresh; manual hold process for unique high-value items |
| Risk | Payment gateway not fully PCI-compliant at launch | Low / High | Platform Vendor | Independent compliance review scheduled 3 weeks pre-launch; go-live gated on sign-off |
| Risk | Launch-week traffic spike causes site slowdowns or checkout failures | Medium / Medium | Platform Vendor | Load testing before launch; hosting plan sized for 5x expected traffic |
| Risk | Staff unfamiliar with BOPIS fulfillment workflow causes pickup delays | Medium / Medium | Store Manager | Dedicated fulfillment training; dry-run of pickup process before launch |
| Assumption | Selected platform supports real-time two-way inventory sync with existing POS | — | Platform Vendor | Confirmed via vendor technical discovery and sandbox test |
| Assumption | Product photography can be completed in-house with vendor guidance | — | Marketing Lead | Photography timeline validated against catalog size |
| Issue | Example: initial photography vendor quote exceeded budget | — | Marketing Lead | Moved photography in-house with a rented lighting kit; saved ~$1,800 |
| Dependency | Full product catalog and photography must be complete before site can launch | — | Marketing Lead | Catalog build scheduled to finish 2 weeks before go-live, with buffer |
| Dependency | Payment gateway approval must be received before go-live | — | Platform Vendor | Application submitted in week 2 to allow full processing time |

# 4. Budget Summary

| Category | Planned | Actual | Notes |
| --- | --- | --- | --- |
| E-commerce platform subscription (annual) | $3,600 | $3,600 | On budget |
| Inventory sync & payment integration (dev/vendor) | $14,000 | $15,200 | Additional sync testing for high-value item holds |
| Product photography & catalog build | $6,500 | $4,700 | Moved photography in-house (see Issue log) |
| Payment gateway setup & compliance review | $2,200 | $2,200 | On budget |
| Staff training & fulfillment setup | $1,800 | $1,600 | On budget |
| Launch marketing (email, social, signage) | $3,200 | $3,050 | On budget |
| Contingency (10%) | $5,200 | $3,400 | Partially used to cover sync testing |
| TOTAL | $52,000 (incl. contingency: est. above) | $33,750 | Actuals reflect committed spend through go-live |

# 5. Communications Plan

| Audience | Channel | Frequency | Content |
| --- | --- | --- | --- |
| Store Owner / GM | In-person / email status report | Weekly | Overall status, budget, risks, decisions needed |
| Store Manager | In-person planning sync | Bi-weekly, weekly closer to launch | Fulfillment readiness, staff scheduling, training status |
| Marketing Lead | Working session | Weekly during content build | Catalog progress, photography, launch campaign plan |
| Platform Vendor | Shared tracker + call | Weekly | Technical milestones, integration testing, blockers |
| Fulfillment Staff | Team huddle + printed guide | At training, then daily during launch week | BOPIS process, escalation path for order issues |
| Customers | Email + in-store signage | 2 weeks before, and day of launch | Launch announcement, how BOPIS works |

# 6. Post-Launch Review

## Outcomes

- Site launched on schedule, within the 16-week timeline and under the approved budget.

- Zero inventory oversell incidents recorded in the first 60 days post-launch.

- Checkout success rate held at 98.6%, above the 98% target, through the first month.

- 29% of online orders were fulfilled via in-store pickup in the first month, ahead of the 25% target.

## What Went Well

- Early vendor discovery calls confirmed real-time inventory sync was feasible before committing budget.

- Moving photography in-house saved budget without compromising catalog quality.

- A fulfillment dry run before launch caught process gaps that would have caused pickup delays.

## Lessons Learned

- Build compliance review timelines with buffer — payment gateway approval processes can take longer than vendors initially estimate.

- Load testing before a marketing push is essential; traffic spikes are hard to predict from historical foot traffic alone.

- A manual hold process for one-of-a-kind items is worth keeping permanently, not just as a launch safeguard.

## Next Steps

Recommended as a Phase 2 candidate: extend BOPIS to same-day pickup, and evaluate a loyalty program integration to connect online and in-store purchase history.

# 7. Program Management Skills Demonstrated

- Project chartering and scope definition

- Stakeholder analysis and engagement planning

- Risk, assumption, issue, and dependency management (RAID)

- Budget planning and variance tracking

- Vendor coordination and technical discovery

- Change management and staff enablement

- Post-launch evaluation and continuous improvement